## Instructions
Streamlined Growth Plan Template - Instructions
Purpose:
This template helps you turn your vision into a clear, step-by-step plan. It ensures your time, money, and energy are spent on actions that deliver real growth without waste.
How to Use:
1. Go to the 'Blank Plan' tab to map out your growth plan from scratch.
2. Define your top three growth goals in the Goals section.
3. Break each goal down into clear, specific actions.
4. Assign an owner, budget, and resources to each action.
5. Track progress weekly in the Progress Tracker tab.
Tabs Overview:
> Blank Plan: A clean sheet ready for you to build your growth plan.
> Demo Plan: A pre-filled example to show how to structure your plan.
> Progress Tracker: A central place to monitor progress and momentum.
> Resource Allocation: Track budgets and avoid overspending.
This template tool was created by Mark Preston of Growth Without The Waste (https://www.growthwithoutthewaste.com/)

## Blank Plan
Goal | Key Action | Owner | Budget (£) | Resources Needed | Deadline | Status

## Demo Plan
Goal | Key Action | Owner | Budget (£) | Resources Needed | Deadline | Status
Increase Customer Retention | Create a follow-up email sequence for new customers | Sarah | 300 | Email software | 15/10/2025 | In Progress
Increase Customer Retention | Launch loyalty program with incentives | Chris | 500 | Loyalty tool | 01/11/2025 | Not Started
Improve Marketing ROI | Audit current ad campaigns and cut low performers | Alex | 0 | Analytics tools | 05/10/2025 | Completed
Improve Marketing ROI | Focus on top-performing ad channel | Alex | 1000 | Design team, ad budget | 20/10/2025 | In Progress
Streamline Onboarding | Create simple onboarding workflow document | Jamie | 0 | Team feedback | 10/10/2025 | Not Started
Streamline Onboarding | Automate first steps using a simple CRM tool | Jamie | 200 | CRM software | 30/10/2025 | Planned

## Progress Tracker
Goal | Action | Owner | Deadline | Status | Notes
Increase Customer Retention | Launch loyalty program with incentives | Chris | 01/11/2025 | Not Started | Researching loyalty tool options
Improve Marketing ROI | Focus on top-performing ad channel | Alex | 20/10/2025 | In Progress | Initial results looking promising

## Resource Allocation
Resource | Purpose | Owner | Cost (£) | Status
Email software | Send automated follow-up emails to customers | Sarah | 300 | Active
Loyalty tool | Manage loyalty program for returning customers | Chris | 500 | Planned
CRM software | Automate onboarding workflow steps | Jamie | 200 | Active