## Instructions
PROCESS BOTTLENECK TRACKER - HOW TO USE
Purpose:
Use this tracker to identify, prioritise, and fix bottlenecks that waste time, money, and energy. Log delays, score their impact, assign an owner, and track resolution. The dashboard updates automatically.
Steps:
1. Go to 'Blank Tracker' and list each bottleneck as it occurs.
2. Complete all columns: Process, Step, Owner, Avg Time (hrs), Delay Cause, Impact Description, Impact Score (1–10), Status, Proposed Solution, Resolution Date.
3. Use Status list: Red = Unresolved, Yellow = In Progress, Green = Resolved.
4. Review the 'Dashboard' for counts and trends. Focus first on items with the highest impact score.
5. Revisit weekly to keep processes smooth and prevent waste from returning.
Tips:
> Be specific. Vague entries lead to vague fixes.
> If a step depends on one person for approval, consider reassigning or adding a fallback approver.
> Celebrate resolved items and document what worked to prevent recurrence.
This tool was created by Mark Preston of Growth Without The Waste (https://www.growthwithoutthewaste.com/)

## Blank Tracker
Process Name | Step Name | Owner | Average Time (hrs) | Delay Cause | Impact Description | Impact Score (1–10) | Status | Proposed Solution | Resolution Date

## Demo Tracker
Process Name | Step Name | Owner | Average Time (hrs) | Delay Cause | Impact Description | Impact Score (1–10) | Status | Proposed Solution | Resolution Date
Customer Onboarding | Collect Client Details | Sarah | 2 | Incomplete client info | Delays onboarding and pushes back first value | 8 | Red | Create client pre-checklist and require before kickoff
Order Fulfilment | Package Order | James | 1 | Packaging shortage | Late deliveries and unhappy customers | 9 | Yellow | Introduce weekly stock review and minimum levels
Marketing Campaign | Content Approval | Linda | 3 | Approval bottleneck | Launches slip and results suffer | 7 | Red | Delegate approval to marketing lead with SLA
Product Development | Testing | Alex | 5 | Testing backlog | Two-week delay to release cycle | 10 | Yellow | Add part-time tester and automate regression tests
Customer Support | Ticket Resolution | Maria | 4 | Manual replies to common queries | Team overloaded and slower response times | 6 | Green | Add FAQs and auto-routing by topic | 2025-09-10
Billing | Invoice Generation | Priya | 1 | Manual data entry | Errors and rework increase cycle time | 6 | Yellow | Connect CRM to invoicing and standardise fields
Sales | Lead Handover | Tom | 2 | Missing info from marketing | Prospect confusion and lost deals | 8 | Red | Define MQL checklist and shared handover form

## Dashboard
PROCESS BOTTLENECK DASHBOARD
Status | Count (All Trackers)
Red | 3
Yellow | 3
Green | 1
Total Unresolved (Red + Yellow) | 6
Resolved This Month (Green with date in current month) | 0
Average Impact Score (All) | 7.7143