## Instructions
Priority Roadmap Template by Growth Without The Waste (https://www.growthwithoutthewaste.com)
Instructions
Welcome to the Priority Roadmap Template.
Purpose: Help you turn ideas into a clear, step-by-step plan for growth.
How to Use:
1. Go to the 'Blank Roadmap' tab.
2. Identify your top three priorities for the next 90 days.
3. For each priority, list the key projects needed to achieve it.
4. Break each project into specific, actionable steps.
5. Assign each action step to a team member and set a clear deadline.
6. Update the 'Status' column as tasks move from Not Started → In Progress → Completed.
Tips:
> Keep action steps small and clear. Each should be completable in 1-2 weeks.
> Use this roadmap in team meetings to keep everyone aligned.
> Revisit and update weekly to track progress and adjust priorities.

## Blank Roadmap
Priority | Project | Action Step | Owner | Deadline | Status | Notes

## Demo Example
Priority | Project | Action Step | Owner | Deadline | Status | Notes
Launch Referral Programme | Build referral landing page | Write copy for referral landing page | Sarah | 15 Mar | In Progress | Key to driving word-of-mouth growth
Launch Referral Programme | Build referral landing page | Design referral page layout | Tom | 20 Mar | Not Started | Visuals must match brand style
Launch Referral Programme | Promote referral programme | Draft email campaign to launch programme | Alex | 22 Mar | Not Started | Segment list for engaged customers
Improve Customer Onboarding | Create onboarding materials | Record welcome video for new customers | Alex | 18 Mar | Completed | Include brand story in video
Improve Customer Onboarding | Create onboarding materials | Design onboarding email templates | Sarah | 20 Mar | In Progress | Test emails with small customer group
Improve Customer Onboarding | Train team on process | Host training session for customer support team | Tom | 22 Mar | Not Started | Record session for future hires
Increase Lead Conversion Rate | Optimise sales funnel | Review current sales funnel and identify drop-off points | Mark | 16 Mar | Not Started | High impact if successful
Increase Lead Conversion Rate | Optimise sales funnel | Create improved call-to-action buttons | Sarah | 19 Mar | In Progress | Use contrasting colours for CTA buttons
Increase Lead Conversion Rate | Run A/B test on checkout page | Analyse test results and implement winning variation | Tom | 25 Mar | Not Started | Monitor closely during test period